## Slide 1: Commercial Due Diligence Training & Templates
By Former Deloitte and McKinsey Management Consultants
Confidential

## Slide 2: Table of Contents
Key steps to follow during your CDD Project
Templates you can easily reused for your own project
1
2

## Slide 3: Table of Contents
Key steps to follow during your CDD Project
Templates you can easily reused for your own project
1
2

## Slide 4: Example of CDD Project Plan
Days
M T W T F M T W T F M T W T F M
Week 1
Week 2
Week 3
Step 1: Background Documents
Step 3: Management meeting
Step 2: Internal Kick-Off
Step 4: Analysis of management data
Step 5: Desk research
Step 7: Financial Modeling
Step 6: Interviews
Step 8: Report preparation and presentation

## Slide 5: Step 1: Identify, gather and read background documents
 | What is it? | Why is it useful?
Information Memorandum | Sale document prepared by Vendor and/or management | Management views, industry context, business overview, historical performance and projections, strategy
Vendor Due Diligence | Financial and sometimes Commercial Due Diligence prepared by advisers to the Vendor | Financial - more detail on business activities, performance, the market and financial position. Commercial – review of market, competitors, customers and a view/rationale behind the business projections. Be wary of VDDs – they can mislead or try to ‘dress up a business’
Specialist market reports | Supplemental specialist reports – e.g. property, environmental, expert and technical reports | More detail on the business in key areas. Tends to be specialist in nature and may require similarly specialist reviewers
VDD presentations | Presentations by report authors with opportunity for Q&A | Chance to ask questions and challenge VDD (approach, data, who spoke to, conclusions). Prepare questions in advance and usually only get one or two chances
Management presentation | Presentation by Management with opportunity for Q&A | Chance to hear Management’s views in their words, form a view on them and ask questions. Usually get one chance so prepare beforehand and work with client/advisers to form a joined-up set of questions and meeting strategy
Trading update | Latest trading performance, often an appendix of the VDD | Up-to-date information on business performance. Beware if this looks late or suspect and ask yourself why
Possible documents involved in a CDD

## Slide 6: Step 2: Internal Kick-off
Meet your team
Establish key role and responsibilities
Ensure a shared understanding of the question we try to answer
Understand the context of the project leveraging the documents read prior to the meeting
Create logic trees to break down the problem into pieces
Run through the scope
Create hypothesis tree including our key hypothesis and assumptions
Talk through the “blank pack”
Present your plan of actions with the “what”, “How”, “Who” and “When”
Discuss key challenges
Prepare for the management meeting
Objectives
Ensure that everyone has an open mind
Ensure that everyone has a shared understanding of what needs to achieve and how
It is important to be well-rested as a CDD project can be intense
Tips

## Slide 7: Step 3: Management meeting
Introduce your team and build a relationship with the management team
Hear the management team describe their business and future plans
Ask questions to the management to clarify key points
Build an understanding of what management data might be available and submit a data request
Objectives
Ask your consultant to take notes and write down a minutes after the meeting
Bring a USB key
Tips

## Slide 8: Step 4: Analysis of Management Data
Management Data Analysis
Tips
Objectives:
  Extracting management data and carry out detailed data analysis
  To build a detailed view of how the company has been performing
  To understand how management have built up their forecasts
  To identify key areas that require probing with management or through market research
  Method:
  Via an excel spreadsheet
  Outputs:
  Chart-Driven Slides that may be included in the final presentation
Quickly draw up data request based on the assumptions you try to validate or invalidate
Sometimes it may be more efficient to ask the management team to request data on your behalf
Analyse initial data by product, business unit, customer, channel, geography, etc.
Understand Management’s forecast model and its underlying assumptions in details
Create chart driven slides to facilitate understanding
If you can’t access some key data, let the management team know asap

## Slide 9: Step 5: Desk Research
Desk research
Tips
Objectives:
  To identify and gather key sources of information on the industry and company (e.g. Industry report, experts, publications, Industry association, and press comments)
  Method:
  By searching on the internet, leveraging the “Data Research” team of your company, or by contacting companies such as RMI
  Outputs:
  Quantitative and qualitative data on the industry and the company
Triangulate: don’t rely just on one source of information
Note all sources of data in you report or in your financial model
Be tenuous as gathering data can be a fastidious task

## Slide 10: Step 6: Interviews
Interviews
Tips
Objectives:
  Gather primary data
  To capture views/opinions on the industry and company
  To ask questions on a specific topic
  To gain data which may not already exist or may be out of date
  Method:
  Interviews with Customers, Suppliers, Partners, Competitors, Industry experts, Regulators, etc.
  Outputs:
  Interview minutes including summary of views and opinions and key quotations
Agree with the management on interviewee list
Organize interviews as soon as possible as people’s agenda can be full
When relevant, ask client to set up the interviews in order to ensure better engagement from the interviewees
Prepare an interview guideline including context, objective, key topics and key questions you want to ask
Be clear on the cover story you are using
Keep questions short
Ask one question at a time
Be neutral in the way you ask questions
Do the least important interview first as a practice
Write up your notes asap, you easily forget
Have a separate excel sheet for quantitative responses
Be careful to maintain confidentiality
Ask if you can call back later if you need any clarification
Identify additional interviewees in order to drill down key areas

## Slide 11: Step 7: Financial Modelling
Interviews
Tips
Objectives:
  To test the impact of varying key drivers or assumptions of the business model. No need to create a new financial model if the one created by the management makes sense.
  Method:
  Understand the key assumptions and drivers used by the Management to forecast revenue and cost
  Flex the Financial Model key assumptions based on the input of your interviews and Desk research
  Outputs:
  The Financial Model should be easy to understand and used by someone else than you
  For more details on how to create a Financial Model using the proper business norms and rules, please click on the link below when you are using the “Slideshow” mode:
    http://www.slidebooks.com/collections/business-templates-1/products/financial-model
Use at least 3 Excel sheets: 1 sheet for your inputs and assumptions, 1 sheet for the calculations and 1 sheet for your output
Avoid hard coding data. If you have no choice but to hard code some data, use a blue font
Take a step back from time to time to ensure that you don’t forget the bigger picture and what you try to achieve

## Slide 12: Step 8: Report
Interviews
Tips
Objectives:
  The report must answer the initial question in a structured way
  The question can be for example:
    Are the forecast reasonable?
    Is the target company healthy?
  Method:
  A “ghost” report is usually created at the beginning of the project
  The structure of the report usually follow the structure of the Hypothesis tree
  The competition of each slide is allocated to someone within the team
  Someone is responsible for updating the report based on the different inputs of each project member
  Outputs:
  A structured report including quantitative and qualitative slides and using an inductive approach and the pyramid principle
  For more details on how to create a report using an inductive approach and the pyramid principle, please click on the link below when you are using the “Slideshow” mode:
    http://www.slidebooks.com/collections/business-templates-1/products/pyramid-principle
Use a straight forward language easy to understand
Be careful with the words you use. For example, instead of saying the management forecasts are not achievable, say that the forecasts are not consistence with evidence
Create an executive summary at the beginning of the presentation

## Slide 13: Table of Contents
Key steps to follow during your CDD Project
Templates you can easily reused for your own project
1
2

## Slide 14: Slide Template to present your team
Insert name and position
Insert name and position
Insert name and position
Insert key role and responsibilities
Insert key role and responsibilities
Insert name and position
Insert key role and responsibilities
Insert key role and responsibilities
Insert key role and responsibilities
Insert key role and responsibilities

## Slide 15: Slide template to present your CDD Project Plan
Days
M T W T F M T W T F M T W T F M
Week 1
Week 2
Week 3
Step 1: Background Documents
Step 3: Management meeting
Step 2: Internal Kick-Off
Step 4: Analysis of management data
Step 5: Desk research
Step 7: Financial Modelling
Step 6: Interviews
Step 8: Report preparation and presentation
Edit time frame and the name of your key steps depending on your project plan requirement

## Slide 16: Slide Template to create a logic tree or hypothesis tree
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text

## Slide 17: Slide Template to create a logic tree or hypothesis tree
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text

## Slide 18: Slide Template to create a logic tree or hypothesis tree
Insert your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text
Your text

## Slide 19: Slide Template to create an interview minute
Insert Key message
Insert details supporting the key message
Insert quotations using an italic font
Interview with John Dana
Minutes
Insert Key message
Insert details supporting the key message
Insert quotations using an italic font
Insert Key message
Insert details supporting the key message
Insert quotations using an italic font

## Slide 20: Slide Template to create an executive summary
Insert your own text
Insert your own text
Insert your own text
Insert your own text
Insert your own text
Insert your own text
Insert your own text
Insert your own text
Question
Answer
Reason #1
Reason #2
Reason #3

## Slide 21: Slide Template to compare the target company with its key competitors
20
15
10
5
0
-5
A
B
C
Gaining market share
Losing market share
Average
market
growth
0
10
20
30
40
50
Company Growth (%)
Market Share (%)
= $ xx million in sales
Insert your key message
60
D

## Slide 22: Slide Template to present the company’s revenue and profit forecast
Insert your key message
Chart: 
| 2014 | 2015 | 2016 | 2017 | 2018
Revenue | 1 | 1 | 2 | 3 | 4
Profit | 0.5 | 0.5 | 1 | 2 | 3
Revenue and Profit forecast

## Slide 23: Slide Template to create a revenue bridge using a waterfall chart
Insert your own comments related to the revenue bridge or waterfall chart on the left
Insert your own comments related to the revenue bridge or waterfall chart on the left
Insert your own comments related to the Insert your own comments related to the revenue bridge or waterfall chart on the left
Insert your own comments related to the revenue bridge or waterfall chart on the left
Insert your own comments related to the revenue bridge or waterfall chart on the left
Insert your own comments related to the revenue bridge or waterfall chart on the left
Insert your own comments related to the revenue bridge or waterfall chart on the left
revenue bridge or waterfall chart on the left
Insert your own comments related to the revenue bridge or waterfall chart on the left
Open the Excel sheet “Commercial Due Diligence_Charts” to access the chart
Revenue bridge
Comments

## Slide 24: Slide Template to create a revenue bridge using a waterfall chart
Insert the key insight of this chart in this speech bubble
Insert the key insight of this chart in this speech bubble
Insert the key insight of this chart in this speech bubble
Open the Excel sheet “Commercial Due Diligence_Charts” to access the chart

## Slide 25: Slide Template to present your revenue forecast and CAGR
Revenue CAGR of 8% between 2015 and 2020
Estimate based on revenue driver 1, driver 2 and driver 3
Open the Excel sheet “Commercial Due Diligence_Charts” to access the chart

## Slide 26: Slide Template to create a CAGR tree which represents a high level view of the Target’s financial model
A Revenue CAGR tree is a high-level view of the Target’s financial model. It includes the key revenue drivers and assumptions
The revenue can be split based on products, Business Units, geography, customers, etc
A Revenue CAGR tree shows past and projected revenue growth
A Revenue CAGR tree represents the Target’s management projection
CAGR tree
Comments
CAGR 2010-2015
Key
Value in 2015
CAGR 2015-2020
xx%
Net Sales
€xxm
xx%
xx%
Sales B
€ xxm
xx%
xx%
Sales A
€xxm
xx%
xx%
Driver A1
xx
xx%
xx%
Driver A2
xx
xx%
xx%
Driver B1
xx
xx%
xx%
Driver B2
xx
xx%
Xx%
Driver A3
xx
xx%
= Key assumption
X
+
+
+
+
xx%
Sales C
€ xxm
xx%
xx%
Driver C1
xx
xx%
xx%
Driver C2
xx
xx%
x
Insert your own text and figures

## Slide 27: Slide Template to assess the Management’s revenue projection
In order to assess the management revenue projection, you need to identify and analyse each key revenue driver
To analyse the key revenue drivers you need to analyse the Company, the Market and the key Competitors
Based on this analysis, you should be able to assess whether or no the assumptions are:
  Conservative: your analysis shows that the greater growth is possible
  Reasonable: your analysis is in line with the assumptions
  Aggressive: your analysis doesn’t support Management assumptions
  And finally, based on the assessment of each key revenue driver, you can consolidate and provide an overall assessment
CAGR tree - Key drivers
Comments
Net Sales
B
A
x%
Driver A1
x
x%
x%
Driver A2
x
x%
x%
Driver B1
x
x%
x%
Driver B2
x
x%
X%
Driver A3
x
x%
+
+
+
+
C
x%
Driver C1
x
x%
x%
Driver C2
x
x%
x
Reasonable: ...
Conservative: ...
Conservative: ...
Aggressive: ...
Reasonable: ...
Reasonable: ...
Conservative: ...
PS: The same way you have a Revenue CAGR Tree, you will probably need to create an EBITDA CAGR Tree
+

## Slide 28: Interested in more than 1 Toolkit? Access all our Toolkits for half the price with our Gold Access
Gold Access
Click here to learn more

## Slide 29: Thanks for your attention!
www.domontconsulting.com