## Slide 1: Post Merger Integration Strategy and High-Level Plan
CEO: insert your own text
Chief Strategy Officer: insert your own text
Date: insert your own text
Version: insert your own text
Contact Email: insert your own text
Guide
Replace the logo by your own logo
Replace the text by your own text. Don’t hesitate to customize this text based on the specificities of your company

## Slide 2: Guide
You can use this deliverable directly for your own purposes. You simply need to insert your logo and adjust the slides based on the specificities of your organization.
Please note that this document also includes many slides with best practices, tutorials and real-life examples to help you adjust this deliverable based on the specificities of your organization. These slides have an orange rectangle in the top-right corner. You may decide to delete these slides as they are mainly there to help you fill in the rest of the deliverable. Before you do, copy and paste this document so you always have the original version in case you need it.
Many of the real-life examples are from a Digital Transformation Business Case presented to the Board of one of our clients, a leading European retail bank. The objective was to convince the Board to invest $100 million in a Digital Transformation Program. The name and data have been changed for confidentiality reasons.

## Slide 3: This deliverable will zoom on the phase I of the Post Merger Integration (PMI) 3-Phase Approach
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Status of the post-merger integration high-level plan
Status of the detailed integration plan
Status of the integration and synergy initiatives plan
Status of the change management strategy and plan
Status of the communication strategy and plan
Status of the culture integration strategy and plan
Status of the risk management strategy and plan
Status of staffing and the retention plan
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Detailed integration plan including the Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 4: This deliverable will zoom on the phase I of the Post Merger Integration (PMI) 3-Phase Approach
Tutorial
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Status of the post-merger integration high-level plan
Status of the detailed integration plan
Status of the integration and synergy initiatives plan
Status of the change management strategy and plan
Status of the communication strategy and plan
Status of the culture integration strategy and plan
Status of the risk management strategy and plan
Status of staffing and the retention plan
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Detailed integration plan including the Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan
Feel free to reuse and customize the approach based on the specificities of your newly combined organization

## Slide 5: Table of contents
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Status of the post-merger integration high-level plan
Status of the detailed integration plan
Status of the integration and synergy initiatives plan
Status of the change management strategy and plan
Status of the communication strategy and plan
Status of the culture integration strategy and plan
Status of the risk management strategy and plan
Status of staffing and the retention plan
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Detailed integration plan including the Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 6: Table of contents
You can decide to zoom on each step individually, or you can decide to zoom on multiple steps at once. This will depend on the number of slides you have for each step, and how the steps are closely related
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Status of the post-merger integration high-level plan
Status of the detailed integration plan
Status of the integration and synergy initiatives plan
Status of the change management strategy and plan
Status of the communication strategy and plan
Status of the culture integration strategy and plan
Status of the risk management strategy and plan
Status of staffing and the retention plan
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Detailed integration plan including the Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan
Tutorial

## Slide 7: Our merger strategic objectives are:
1
Replace this text by your own text
2
Replace this text by your own text
3
Replace this text by your own text
4
Replace this text by your own text
5
Replace this text by your own text
6
Replace this text by your own text

## Slide 8: Our merger strategic objectives are:
1
Replace this text by your own text
2
Replace this text by your own text
3
Replace this text by your own text
4
Replace this text by your own text
5
Replace this text by your own text
6
Replace this text by your own text
Don’t reinvent the wheel here. Most of the strategic objectives should have already been written prior to the deal.
Tutorial

## Slide 9: The most common merger strategic objectives are:
1
Gaining economies of scale
2
Entering a new country
3
Entering a new market
4
Increasing the company product or service portfolio
5
Increasing market share by acquiring one of your competitors (horizontal integration)
6
Becoming a key player in an industry by acquiring one of your suppliers or clients (vertical integration)

## Slide 10: The most common merger strategic objectives are:
1
Gaining economies of scale
2
Entering a new country
3
Entering a new market
4
Increasing the company product or service portfolio
5
Increasing market share by acquiring one of your competitors (horizontal integration)
6
Becoming a key player in an industry by acquiring one of your suppliers or clients (vertical integration)
Example we used during a PMI consulting project we did for a Global Fortune 1000 firm.

## Slide 11: We decided to create an Integration Management Office that will be responsible for the success of the integration
The Integration Management Office will oversee the post Merger Integration and be responsible for the success of the integration. It includes 7 [replace this number by your own number] executives representing both [insert name of the acquiring company] and [insert name of the acquired company]:
Integration Management Officer
[Insert name]
Integration and Synergy Initiatives
[Insert name]
Change Management
[Insert name]
Culture
[Insert name]
Risk Management
[Insert name]
Communication
[Insert name]
Training
[Insert name]

## Slide 12: We decided to create an Integration Management Office that will be responsible for the success of the integration
The Integration Management Office will oversee the post Merger Integration and be responsible for the success of the integration. It includes 7 [replace this number by your own number] executives representing both [insert name of the acquiring company] and [insert name of the acquired company]:
Integration Management Officer
[Insert name]
Integration and Synergy Initiatives
[Insert name]
Change Management
[Insert name]
Culture
[Insert name]
Risk Management
[Insert name]
Communication
[Insert name]
Training
[Insert name]
This is only an example. You may decide to emphasize different areas and adjust the size of the integration Management Office
Best practice

## Slide 13: We identified 8 [insert your own number] post merger integration guiding principles
1
Insert your own guiding principle
2
Insert your own guiding principle
3
Insert your own guiding principle
4
Insert your own guiding principle
7
Insert your own guiding principle
5
Insert your own guiding principle
8
Insert your own guiding principle
6
Insert your own guiding principle

## Slide 14: We identified 8 [insert your own number] post merger integration guiding principles
1
Be clear on the strategic objectives of the deal
2
Ground the integration in the objectives of the deal
3
Be clear on your synergy baseline and synergy targets
4
Create a robust integration plan to reach the strategic objectives of the deal and the synergy targets
7
Ensure cultural fit
5
Search for synergies in every function of the newly created organization
8
Maintain business momentum
6
Communicate on a regular basis to all stakeholders
Real-life example

## Slide 15: Table of contents
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Status of the post-merger integration high-level plan
Status of the detailed integration plan
Status of the integration and synergy initiatives plan
Status of the change management strategy and plan
Status of the communication strategy and plan
Status of the culture integration strategy and plan
Status of the risk management strategy and plan
Status of staffing and the retention plan
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Detailed integration plan including the Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 16: Our High-Level Plan mirrors all the steps included in our 3-phase approach
Our high-level plan includes:
Phases
Steps
Owners
Due dates
Statuses
Timeframes
You’ll see in the next slides our high-level plan in Powerpoint. We also created a more practical version of our High-Level Plan in the Excel document called “High-Level Plan”, located in the folder “Phase I - Strategy and High-Level Plan”.

## Slide 17: Our High-Level Plan mirrors all the steps included in our 3-phase approach
Our high-level plan includes:
Phases
Steps
Owners
Due dates
Statuses
Timeframes
You’ll see in the next slides our high-level plan in Powerpoint. We also created a more practical version of our High-Level Plan in the Excel document called “High-Level Plan”, located in the folder “Phase I - Strategy and High-Level Plan”.
Tutorial

## Slide 18: High-Level Plan – Phase 1
 | Owner | Due date | Status | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Define & communicate the Strategy & High-Level Plan | AD | March 12 | Done |  |  |  |  |  |  |  |  |  |  |  | 
Merger strategic objectives | Aurelien F. | Jan 20 | Done |  |  |  |  |  |  |  |  |  |  |  | 
Integration management office | Christian G. | Jan 20 | Done |  |  |  |  |  |  |  |  |  |  |  | 
Guiding principles | George P. | Jan 20 | Done |  |  |  |  |  |  |  |  |  |  |  | 
Post merger integration high-level plan | George P. | Feb 15 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Organizational structure (Top layers) | George P. | Feb 15 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Top management appointment | George P. | Feb 15 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Training to help managers set up their team | John D. | Feb 28 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Integrated synergy baseline | John D. | Feb 28 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Synergy targets | John D. | Feb 28 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Potential integration & synergy initiatives | John D. | Feb 28 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Business cases and financial models | John D. | Feb 28 | Late |  |  |  |  |  |  |  |  |  |  |  | 
Integration & synergy initiatives prioritization | John D. | Feb 28 | Late |  |  |  |  |  |  |  |  |  |  |  | 
2021

## Slide 19: High-Level Plan – Phase 1
 | Owner | Due date | Status | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Define & communicate the Strategy & High-Level Plan | AD | March 12 | Done |  |  |  |  |  |  |  |  |  |  |  | 
Merger strategic objectives | Aurelien F. | Jan 20 | Done |  |  |  |  |  |  |  |  |  |  |  | 
Integration management office | Christian G. | Jan 20 | Done |  |  |  |  |  |  |  |  |  |  |  | 
Guiding principles | George P. | Jan 20 | Done |  |  |  |  |  |  |  |  |  |  |  | 
Post merger integration high-level plan | George P. | Feb 15 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Organizational structure (Top layers) | George P. | Feb 15 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Top management appointment | George P. | Feb 15 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Training to help managers set up their team | John D. | Feb 28 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Integrated synergy baseline | John D. | Feb 28 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Synergy targets | John D. | Feb 28 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Potential integration & synergy initiatives | John D. | Feb 28 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Business cases and financial models | John D. | Feb 28 | Late |  |  |  |  |  |  |  |  |  |  |  | 
Integration & synergy initiatives prioritization | John D. | Feb 28 | Late |  |  |  |  |  |  |  |  |  |  |  | 
2021
This Powerpoint version of the high-level plan is useful for an executive committee or a board meeting. But other than that, we highly recommend the use of the Excel version, which is a lot more practical.
Usually, our one source of truth is the Excel version. And prior to an important meeting with executives, we will extract the section of the plan we want to emphasize. We also like to keep in our pocket the Excel version during the meeting, but we will only display it if needed.
Best practice

## Slide 20: High-Level Plan – Phase 2
 | Owner | Due date | Status | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Develop & Communicate the Detailed Plans | AD | March 12 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Day 1 readiness checklist | Aurelien F. | Jan 20 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Integration & synergy initiatives plan | Christian G. | Feb 28 | Late |  |  |  |  |  |  |  |  |  |  |  | 
Change management strategy and plan | George P. | March 31 | Done |  |  |  |  |  |  |  |  |  |  |  | 
Communication strategy and plan | George P. | March 31 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Culture integration strategy and plan | Christian G. | March 31 | Late |  |  |  |  |  |  |  |  |  |  |  | 
Risk management strategy and plan | George P. | March 31 | Done |  |  |  |  |  |  |  |  |  |  |  | 
Staffing & retention plan | George P. | March 31 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
2021

## Slide 21: High-Level Plan – Phase 3
 | Owner | Due date | Status | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Implement & Monitor | AD | March 12 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Post merger integration high-level plan | Aurelien F. | Dec 5 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Day 1 readiness checklist | Christian G. | Dec 5 | Late |  |  |  |  |  |  |  |  |  |  |  | 
Integration & synergy initiatives plan | George P. | Dec 5 | Done |  |  |  |  |  |  |  |  |  |  |  | 
Change management strategy and plan | George P. | Dec 5 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Communication strategy and plan | Christian G. | Dec 5 | Late |  |  |  |  |  |  |  |  |  |  |  | 
Culture integration strategy and plan | George P. | Dec 5 | Done |  |  |  |  |  |  |  |  |  |  |  | 
Risk management strategy and plan | George P. | Dec 5 | Done |  |  |  |  |  |  |  |  |  |  |  | 
Staffing & retention plan | George P. | Dec 5 | Done |  |  |  |  |  |  |  |  |  |  |  | 
Integration lessons learned | George P. | Dec 10 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
Institutionalization of the updated PMI Toolkit | George P. | Dec 20 | On Track |  |  |  |  |  |  |  |  |  |  |  | 
2021

## Slide 22: Table of contents
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Status of the post-merger integration high-level plan
Status of the detailed integration plan
Status of the integration and synergy initiatives plan
Status of the change management strategy and plan
Status of the communication strategy and plan
Status of the culture integration strategy and plan
Status of the risk management strategy and plan
Status of staffing and the retention plan
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Detailed integration plan including the Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 23: Current organizational structure (Top layers)
CEO
Chief Financial Officer
Business Unit 1 CEO
Business Unit 2 CEO
Chief Technology Officer
Chief Operating Officer
Chief Technology Officer
Chief Financial Officer
Chief Operating Officer

## Slide 24: Target organizational structure (Top layers)
CEO
Business Unit 1
CFO
Business Unit 2
CFO
Business Unit 1
CTO
Business Unit 1
COO
Business Unit 2
CTO
Business Unit 2
COO
Chief Financial Officer
Chief Technology Officer
Chief Operating Officer
Chief Marketing Officer
Business Unit 1
CMO
Business Unit 2
CMO
Additional template

## Slide 25: Top management appointment
CEO
John Smith
Business Unit 1
CFO
Mike G.
Business Unit 2
CFO
Pierre G.
Business Unit 1
CTO
John V.
Business Unit 1
COO
Claire H.
Business Unit 2
CTO
Claire G.
Business Unit 2
COO
Elizabeth G.
Chief Financial Officer
Pauline Newman
Chief Technology Officer
Christopher Han
Chief Operating Officer
Raphael Domino
Chief Marketing Officer
Caty Spheran
Business Unit 1
CMO
Sebastian K.
Business Unit 2
CMO
Marc P.
Additional template

## Slide 26: Table of contents
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Status of the post-merger integration high-level plan
Status of the detailed integration plan
Status of the integration and synergy initiatives plan
Status of the change management strategy and plan
Status of the communication strategy and plan
Status of the culture integration strategy and plan
Status of the risk management strategy and plan
Status of staffing and the retention plan
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Detailed integration plan including the Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 27: Table of contents
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Status of the post-merger integration high-level plan
Status of the detailed integration plan
Status of the integration and synergy initiatives plan
Status of the change management strategy and plan
Status of the communication strategy and plan
Status of the culture integration strategy and plan
Status of the risk management strategy and plan
Status of staffing and the retention plan
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Detailed integration plan including the Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan
Tutorial
There will be a high level of stress within the different teams. Training each manager on how to set up their team while understanding the psychological state of their staff will be key to make the transition as smooth as possible.

## Slide 28: Example of training to help managers set their new teams up for success

## Slide 29: Understanding people’s rational thinking and emotions
As humans we have 2 drivers – our Hearts & Minds. As a leader you need to appeal to both the heart (emotions) and mind (rational thinking) in order to support people through change.
The 2 tonne elephant is our emotional side being tenuously controlled by a much smaller rider, who represents our rational side.
So if your focus is to lead change, you need to appeal to both the heart and mind in order to create the required engagement to successfully drive the change.
To satisfy the elephant which is much bigger, you will have to understand and consider emotions.
Rational Side
Emotional Side

## Slide 30: Understanding people’s reaction to change
Change is about losing something of value, familiarity and comfort. This curve will be used to help us understand how people react to change, so that you can help them make their own personal transitions and make sure that they have the help and support they need.
We all react differently when impacted by change, some take longer than others to work through it and some don’t experience the depth of the curve as deeply as others.
As a leader, it helps to understand how people will react to change, so that you can help and support them while they transition through this curve from Denial to Commitment.
The “idea clouds” on the curve indicate how you can help your people. i.e. If they show resistance, then focus on listening.
Based on the change curve, the higher the impact the more likely your team will experience the change more deeply.
You may notice however, some of your new team members may be “early adopters” and get on board with change really
quickly. Discovering where your team members are at in their personal transition, and meeting them there, is a perfect start to your role of helping and supporting others
The change curve is a powerful model used to understand the stages of personal transition.
The Change Curve
Emotional
Self
Rational
Self

## Slide 31: Understanding the impact of change on your team members
Based on where your team members have come from, varying levels of impact may be experienced. This matrix will help you identify the impact of the restructure on individuals in your team – this awareness will help you consider appropriate activities to support them on a personal level.
Nil or Low
(e.g. No change)
Change of Role
Change of environment
(Company, Division, BU, and Reporting Line)
High
(e.g. Change of company)
Nil
New
Role
Medium
(e.g. Change of Team or Function)
Small
changes
Jack
John
Lisa
Low Impact
Medium Impact
High Impact
Legend:

## Slide 32: Forming a team taking into account of the 4 stages of team development
Forming a team takes time, and members often go through recognisable stages as they change from being collections of strangers to united groups with common goals.
FORMING
STORMING
NORMING
PERFORMING
Intragroup conflict, distrust and knowledge hoarding
Close relationships and cohesiveness, knowledge sharing and collaboration
Team members work toward getting their job done
Each step builds on the previous one
Skipping any step impacts performing negatively
With every new challenge, the process repeats
  Set a mission
  Set goals
  Establish roles
  Leader direction
  Develop a team Charter
  Define rewards
  Take risks
  Gather regularly to work on common tasks
  Assert leadership
  Decide to be ONE team
Actions
Forming to Storming
  Leader:
  Reinforce behaviours
  Create positive environment
  Ask for and expect results
  Recognise wins
  Team:
  Agree on individual roles
  Buy into objectives and actions
  Listen to each other
  Support each other
  Ask for feedback
  Honour commitments
Actions
Storming to Norming
  Maintain traditions
  Praise and flatter each other
  Self-evaluate without a fuss
  Share leadership role in team based on who does what the best
  Share rewards and success
  Communicate. Always
  Share responsibility
  Delegate and commit
  Keep raising the bar
  Hire “right people for the right role” mindset
Actions
Norming to Performing
Knowledge is hidden and trust is unknown

## Slide 33: Table of contents
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Status of the post-merger integration high-level plan
Status of the detailed integration plan
Status of the integration and synergy initiatives plan
Status of the change management strategy and plan
Status of the communication strategy and plan
Status of the culture integration strategy and plan
Status of the risk management strategy and plan
Status of staffing and the retention plan
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Detailed integration plan including the Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 34: There are 2 types of synergy: Cost synergy and Revenue synergy
*The break down of the cost synergy and revenue synergy is not comprehensive
Total synergy
Removing people duplication
Removing IT system duplication
Removing process duplication
Cross selling products
Bringing new products or services into new channels
Bringing new products or services geographies
Cost synergy*
Revenue synergy*

## Slide 35: We believe it is very important to create an integrated synergy baseline, which consolidates data from 4 major areas
Market
Financial
People
Operational
Integrated Synergy
Baseline
Progress will be measured based on the integrated synergy baseline

## Slide 36: The main Market data that we will use are:
Market share by product
Market share by Segment
Market share by geography

## Slide 37: The main Financial data are:
Per brand
Per Business Unit or per function
Per product
Per brand
Per function or cost center
Per product
Revenue
Cost

## Slide 38: The main operational data are:
Efficiency & effectiveness metrics
Inventory
Number of units produced

## Slide 39: The main People data are:
Full time employees (FTE), part time employees, contractors and vacancies by:
Business unit
Team
Location
Function
Remuneration, benefits, and redundancy costs

## Slide 40: Table of contents
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Status of the post-merger integration high-level plan
Status of the detailed integration plan
Status of the integration and synergy initiatives plan
Status of the change management strategy and plan
Status of the communication strategy and plan
Status of the culture integration strategy and plan
Status of the risk management strategy and plan
Status of staffing and the retention plan
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Detailed integration plan including the Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 41: It is very important to be as clear as possible on the synergy targets we need to reach
Complexity is the enemy of execution
Tony Robbins

## Slide 42: Our synergy target is $140M [insert your own number] over the next 2 years
Chart: 
| Total Synergies | Cost synergy | Revenue synergy
Invisible dataset | 0 | 40 | 0
Light blue | 100 | 40
Dark Blue | 140
Total synergies Company X wants to achieve
over the next 2 years ($M)

## Slide 43: Our synergy target is $140M [insert your own number] over the next 2 years
Chart: 
| Total Synergies | Cost synergy | Revenue synergy
Invisible dataset | 0 | 40 | 0
Light blue | 100 | 40
Dark Blue | 140
Total synergies Company X wants to achieve
over the next 2 years ($M)
1.Double click on the chart and then click on “Edit Data” and then “Edit data in Excel” to update this Chart
Tutorial

## Slide 44: Breakdown of our synergy target per function
Synergy Target per function ($M)
Chart: 
| Total Synergies | IT | R&D | Procurement | Production | Sales & Marketing
Invisible dataset | 0 | 120 | 90 | 80 | 40 | 0
Light blue | 20 | 30 | 10 | 40 | 40
Dark Blue | 140

## Slide 45: Breakdown of our synergy target per function
Synergy Target per function ($M)
Chart: 
| Total Synergies | IT | R&D | Procurement | Production | Sales & Marketing
Invisible dataset | 0 | 120 | 90 | 80 | 40 | 0
Light blue | 20 | 30 | 10 | 40 | 40
Dark Blue | 140
1.Double click on the chart and then click on “Edit Data” and then “Edit data in Excel” to update this Chart
Tutorial

## Slide 46: Table of contents
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Status of the post-merger integration high-level plan
Status of the detailed integration plan
Status of the integration and synergy initiatives plan
Status of the change management strategy and plan
Status of the communication strategy and plan
Status of the culture integration strategy and plan
Status of the risk management strategy and plan
Status of staffing and the retention plan
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Detailed integration plan including the Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 47: There are 2 types of integration & synergy initiatives
Initiatives facilitating the integration
Initiatives capturing synergies

## Slide 48: There are 2 types of integration & synergy initiatives
Initiatives facilitating the integration
Initiatives capturing synergies
The main objective of these initiatives facilitating the integration is to help the 2 organizations merge smoothly.
For example, creating a welcome day for the employees of the acquired company will not directly capture synergy. However, it will help the employees to transition quickly into the new organization.
The quicker the transition, the sooner we can expect to create the value expected by the shareholders.
The main objective of these initiatives is to capture cost and / or revenue synergies in order to increase the profit of our combined organization. In other words, 1 + 1 should equal 3, not 2.

## Slide 49: We believe that the most common functions where synergies can be achieved are:
Insert your own text and update the icon of the left (e.g. Information Technology)
Insert your own text and update the icon of the left (e.g. Research & Development)
Insert your own text and update the icon of the left (e.g. Procurement)
Insert your own text and update the icon of the left (e.g Production)
Insert your own text and update the icon of the left (e.g. Sales & Marketing)

## Slide 50: Zoom on Information Technology (IT)
In this text box, describe how you will ensure a smooth integration (e.g. Ensure basic connectivity and appropriate security on day one), and what type of synergy you could achieve within this function (e.g. one IT system could be removed due to duplication).

## Slide 51: Zoom on Research & Development (R&D)
In this text box, describe how you will ensure a smooth integration, and what type of synergy you could achieve within this function.

## Slide 52: Zoom on Procurement
In this text box, describe how you will ensure a smooth integration, and what type of synergy you could achieve within this function.

## Slide 53: Zoom on Production
In this text box, describe how you will ensure a smooth integration, and what type of synergy you could achieve within this function.

## Slide 54: Zoom on Sales & Marketing
In this text box, describe how you will ensure a smooth integration, and what type of synergy you could achieve within this function.

## Slide 55: Zoom on Information Technology (IT)
Depending on the industry, IT can generate between 15% and 30% of total synergies. IT also helps the other functions to reach their respective synergies.
To achieve IT synergy target, it is important to:
Create a cross functional IT Integration team
Identify as quickly as possible which IT Systems should be removed due to duplication
Ensure basic connectivity and appropriate security on day one
This slide has been added to give you more information on what to expect for this function

## Slide 56: Zoom on Research & Development (R&D)
R&D synergy can be high, especially in the pharmaceutical industry. The most critical asset in R&D is the personnel, along with their knowledge and expertise.
To achieve R&D synergy target, it is important to:
Identify the expertise and knowledge of both the acquiring company and the acquired company
Decide, depending on the context, to mix R&D teams or keep them separate
Retain critical personnel, along with their knowledge and expertise
This slide has been added to give you more information on what to expect for this function

## Slide 57: Zoom on Procurement
Procurement synergy is mainly achieved by negotiating lower prices with the different suppliers. And lower prices are usually achieved by ordering more goods and services (due to the bigger size of the company) and putting in competition the suppliers used by the acquiring company and the target company. To achieve Procurement synergy target, it is important to:
Decrease the number of suppliers used by the acquiring company and the acquired company
Challenge long established supplier relationships
Identify the “must have” and the “nice to have” for each product and service
This slide has been added to give you more information on what to expect for this function

## Slide 58: Zoom on Production
A merger or an acquisition is often a good timing to review the production strategy of a company. The most common questions that executives will have to answer are:
What is the ideal design for the manufacturing network?
Should we produce internally, or should we outsource?
Which region or country would offer the best “cost-quality” ratio?
This slide has been added to give you more information on what to expect for this function

## Slide 59: Zoom on Sales & Marketing
Sales & Marketing usually have both cost synergy target and revenue synergy target. Achieving these targets require to:
Redefine the value proposition of the company to optimize the complementarity between brands
Optimize the sales organisation structure
Cross sell and/or bring new products or services into new channels or geographies
This slide has been added to give you more information on what to expect for this function

## Slide 60: See below a list of our potential integration & synergy initiatives
Initiatives facilitating the integration
Initiatives capturing synergies
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative
Insert name of the initiative

## Slide 61: Table of contents
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Status of the post-merger integration high-level plan
Status of the detailed integration plan
Status of the integration and synergy initiatives plan
Status of the change management strategy and plan
Status of the communication strategy and plan
Status of the culture integration strategy and plan
Status of the risk management strategy and plan
Status of staffing and the retention plan
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Detailed integration plan including the Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 62: To be able to prioritize our initiatives, a business case has been created for each initiative
Each Business Case has been created in the folder “Business case and financial model”, and provides the following information:
Business Opportunity & Suggested Solution
Project Objectives, Scope & Approach
Project Deliverables & Business Outcomes
Strategic Alignment
Dependencies & Constraints
Risk Assessment & Mitigation
Change Impact Assessment
Project Costs
Benefits
Net Present Value
Key Success Factors & KPIs
In the next slides, you will see a lean business case for our top 5 key initiatives

## Slide 63: To be able to prioritize our initiatives, a business case has been created for each initiative
Each Business Case has been created in the folder “Business case and financial model”, and provides the following information:
Business Opportunity & Suggested Solution
Project Objectives, Scope & Approach
Project Deliverables & Business Outcomes
Strategic Alignment
Dependencies & Constraints
Risk Assessment & Mitigation
Change Impact Assessment
Project Costs
Benefits
Net Present Value
Key Success Factors & KPIs
In the next slides, you will see a lean business case for our top 5 key initiatives
We’ve been using this business case for years. It will make your prioritization process way more professional, and it will increase the quality of your decisions.
It will also help standardize the business case exercise. We’ve noticed so many times big corporations with different business units using their own business case structure and metrics. But how can you choose between a project that has a ROI of 300% and another project that has a Net present value of $10M? You simply can’t. A set of metrics need to be defined and each business case should emphasize the same key metrics, so you can compare the different initiatives
Best practice

## Slide 64: Lean Business Case Project name: Project description:
Change Impact
High Impact
Net Present Value
$8M
Number of Resources
12
Change Manager
John Doe
Cash Flow (US $ millions)
Project Sponsor
John Doe
Intangible Benefits
Insert your own text
Project Costs
$4M
Tangible Benefits
$14M
Project Manager
John Doe
Strategic Alignment
Insert the Strategic Objectives that the project is aligned with

## Slide 65: Lean Business Case Project name: Project description:
Change Impact
High Impact
Net Present Value
$8M
Number of Resources
12
Change Manager
John Doe
Cash Flow (US $ millions)
Project Sponsor
John Doe
Intangible Benefits
Insert your own text
Project Costs
$4M
Tangible Benefits
$14M
Project Manager
John Doe
Strategic Alignment
Insert the Strategic Objectives that the project is aligned with
We often use a lean business case (which is a one-page summary of the entire business case) during the prioritization exercise. Each initiative uses the exact lean business case, so we can easily compare them.
Tutorial

## Slide 66: Lean Business Case Project name: Project description:
Change Impact
High Impact
Net Present Value
$8M
Number of Resources
12
Change Manager
John Doe
Cash Flow (US $ millions)
Project Sponsor
John Doe
Intangible Benefits
Insert your own text
Project Costs
$4M
Tangible Benefits
$14M
Project Manager
John Doe
Strategic Alignment
Insert the Strategic Objectives that the project is aligned with
Of course, this is only an example. Different metrics may be more important for your organization. It really depends on the industry, the culture and the objectives of your organization. Before asking hundreds of people to create their business case, it is important to sit down with your CEO and define what matters to your organization.
Tutorial

## Slide 67: Lean Business Case Project name: Project description:
Change Impact
High Impact
Net Present Value
$8M
Number of Resources
12
Change Manager
John Doe
Cash Flow (US $ millions)
Project Sponsor
John Doe
Intangible Benefits
Insert your own text
Project Costs
$4M
Tangible Benefits
$14M
Project Manager
John Doe
Strategic Alignment
Insert the Strategic Objectives that the project is aligned with

## Slide 68: Lean Business Case Project name: Project description:
Change Impact
High Impact
Net Present Value
$8M
Number of Resources
12
Change Manager
John Doe
Cash Flow (US $ millions)
Project Sponsor
John Doe
Intangible Benefits
Insert your own text
Project Costs
$4M
Tangible Benefits
$14M
Project Manager
John Doe
Strategic Alignment
Insert the Strategic Objectives that the project is aligned with

## Slide 69: Lean Business Case Project name: Project description:
Change Impact
High Impact
Net Present Value
$8M
Number of Resources
12
Change Manager
John Doe
Cash Flow (US $ millions)
Project Sponsor
John Doe
Intangible Benefits
Insert your own text
Project Costs
$4M
Tangible Benefits
$14M
Project Manager
John Doe
Strategic Alignment
Insert the Strategic Objectives that the project is aligned with

## Slide 70: Table of contents
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Status of the post-merger integration high-level plan
Status of the detailed integration plan
Status of the integration and synergy initiatives plan
Status of the change management strategy and plan
Status of the communication strategy and plan
Status of the culture integration strategy and plan
Status of the risk management strategy and plan
Status of staffing and the retention plan
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Detailed integration plan including the Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 71: We used the following prioritization matrix in order to prioritize all our potential integration & synergy initiatives
Our prioritization matrix is based on impact and effort:
Impact
Effort
For the initiatives facilitating the integration: an initiative with a high impact would mean that the initiative is very important in the success of the integration
For the initiatives capturing synergy: an initiative with a high impact would mean that the initiative highly contributes to the achievement of the synergy targets
Ease of implementation
Time frame required
Resources required (Number of people, capital investment, etc.)

## Slide 72: The focus should be on the initiatives that have the greatest impact and require the lowest effort
Impact
Effort
Prioritization matrix
Low
High
Low
High
Longer term initiatives (actively work to reduce required effort)
Initiatives to be prioritized
Unattractive initiatives (do not pursue)
Low value initiatives (pursue opportunistically)

## Slide 73: The focus should be on the initiatives that have the greatest impact and require the lowest effort
Impact
Effort
Prioritization matrix
Low
High
Low
High
Longer term initiatives (actively work to reduce required effort)
Initiatives to be prioritized
Unattractive initiatives (do not pursue)
Low value initiatives (pursue opportunistically)
Please note that what you decide not to do is as important as what you decide to do. A good CEO is someone that is not afraid to say “no”, and focus on the initiatives that will really move the needle. Human and financial resources are limited. How to allocate these resources is critical.
Tutorial

## Slide 74: Prioritization of the initiatives facilitating the integration
Impact
Effort
Low
High
Low
High
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative

## Slide 75: Prioritization of the initiatives capturing synergy
Impact
Effort
Low
High
Low
High
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative
Insert the name of your initiative

## Slide 76: Time now to focus on the Phase II, located in the folder “Phase II - Develop and Communicate the Detailed Plans”
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Status of the post-merger integration high-level plan
Status of the detailed integration plan
Status of the integration and synergy initiatives plan
Status of the change management strategy and plan
Status of the communication strategy and plan
Status of the culture integration strategy and plan
Status of the risk management strategy and plan
Status of staffing and the retention plan
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Detailed integration plan including the Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 77: Interested in more than 1 Toolkit? Access all our Toolkits for half the price with our Gold Access
Gold Access
Click here to learn more

## Slide 78: Thanks for your attention!
www.domontconsulting.com