## Slide 1: Phase III - Implement and Monitor
By ex-McKinsey, Deloitte & BCG Management Consultants
Confidential

## Slide 2: To ensure a proper execution of the integration & synergy initiatives, it is very important to appoint high-caliber initiative owner or project manager
Project Manager
Quality
Cost
Time
Meeting the expectations
Managing a budget and resource limitations
Completing the project in a specific time of frame

The main challenge of the different initiative owners or project managers will be to meet the objectives while balancing the triple constraints of quality, cost and time

## Slide 3: In order to begin the Phase III, you will have to copy paste the highlighted documents below in the folder “Phase III: Implement & Monitor”
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Status of the post-merger integration high-level plan
Status of the detailed integration plan
Status of the integration and synergy initiatives plan
Status of the change management strategy and plan
Status of the communication strategy and plan
Status of the culture integration strategy and plan
Status of the risk management strategy and plan
Status of staffing and the retention plan
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Detailed integration plan including the Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 4: The new single source of truth regarding these documents should now be in the folder “Phase III: Implement & Monitor”
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Status of the post-merger integration high-level plan
Status of the detailed integration plan
Status of the integration and synergy initiatives plan
Status of the change management strategy and plan
Status of the communication strategy and plan
Status of the culture integration strategy and plan
Status of the risk management strategy and plan
Status of staffing and the retention plan
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Detailed integration plan including the Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 5: To follow the progress of the integration & synergy initiatives, a weekly meeting will have to be organized with the owner of each initiative
The initiative owner will have between 1 and 5 minutes to present the progress of their initiatives. The name of each initiative should be easily understood by people who are not working on the initiative. Acronyms or non explicit words shouldn’t be used.
For each initiative, the following topics are usually covered:
The status of the initiative
The planned synergy (if relevant)
The actual synergy reached so far (if relevant)
The deadline
Key risks
Key issues
Key interdependencies

## Slide 6: To facilitate this meeting, we recommend the use of the table below, which should be printed or recreated on the meeting room wall
 | Status | Owner | Planned synergy | Actual synergy reached so far | Deadline | Key Risks | Key Issues | Inter-dependencies
Insert name of the initiative |  | AD |  |  |  |  |  | 
Insert name of the initiative |  | JF |  |  |  |  |  | 
Insert name of the initiative |  | AD |  |  |  |  |  | 
Insert name of the initiative |  | JF |  |  |  |  |  | 
Insert name of the initiative |  | JF |  |  |  |  |  | 
Insert name of the initiative |  | JF |  |  |  |  |  | 
Insert name of the initiative |  | JF |  |  |  |  |  | 
Insert name of the initiative |  | JF |  |  |  |  |  | 
Insert name of the initiative |  | MJ |  |  |  |  |  | 

## Slide 7: Each initiative owner should also create a “one-pager” initiative status report, which provides the next layer of details
An initiative status report provides an overview of the initiative key information that the upper management needs to know.
You will find 3 different templates in the next slides. Feel free to use the one that you prefer.

## Slide 8: Insert the Initiative Name - Status report - 04/10/2021 Insert Author
Insert Project Logo
Insert Company Name & Project Name
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Overall Status
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Time / Deadlines
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Cost / Budget
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Requirement / Quality

## Slide 9: Insert the Initiative Name - Status report - 04/10/2021 Insert Author
Insert Project Logo
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Overall Status
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Time / Deadlines
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Cost / Budget
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Requirement / Quality
  Key Past Milestones
  Key Current Milestones
  Key Future Milestones

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

## Slide 10: Insert the Initiative Name - Status report - 04/10/2021 Insert Author
Insert Project Logo
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Overall Status
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Time / Deadlines
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Cost / Budget
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Requirement / Quality
  Key Past Milestones
  Key Current Milestones
  Key Future Milestones

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

## Slide 11: The new single source of truth regarding these documents should now be in the folder “Phase III: Implement & Monitor”
Phase I: Define & communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan
Post merger integration high-level plan status
Day 1 readiness checklist status
Integration & synergy initiatives plan status
Change management strategy and plan status
Communication strategy and plan status
Culture integration strategy and plan status
Risk management strategy and plan status
Staffing & retention plan status
Integration lessons learned
Institutionalization of the updated PMI Toolkit

## Slide 12: Key lessons learned from our Post Merger Integration
Insert title of the key lesson learned (e.g. Do not underestimate cultural change)
Describe in this box what you’ve learned
Insert title of the key lesson learned
Describe in this box what you’ve learned
Insert title of the key lesson learned
Describe in this box what you’ve learned
Insert title of the key lesson learned
Describe in this box what you’ve learned
Insert title of the key lesson learned
Describe in this box what you’ve learned

## Slide 13: Institutionalization of the updated PMI Toolkit
The PMI Toolkit that you initially purchased should now include many customizations aligned with the specificities of your organization. As a result, it is this updated version of the Toolkit that should now be used as a resource for your next post merger integration.
Make sure to spend some time after your PMI to clean the Toolkit so it is nice and ready to use for your next PMI.

## Slide 14: Thanks for your attention!
www.domontconsulting.com