## Slide 1: Post Merger Integration Toolkit Overview and 3-Phase Approach
Confidential
Created by ex-McKinsey, Deloitte & BCG Strategy Consultants

## Slide 2: Context The advantages & disadvantages of an organic growth strategy.
Organic Growth Strategy
Description
Advantages
Disadvantages
Often perceived as the default growth option for companies, an organic growth strategy relies on developing a company’s internal resources and capabilities
Provides deeper first-hand knowledge that is likely to be internalized in the company
Helps spread investment over time and reduce upfront commitment
There are no availability constraints, that is to say that the company is not dependent on the availability of suitable acquisition targets or potential alliance partners
Strategic independence
Creation of new activities within the existing culture environment
Can be slow, expensive, and risky
Difficult to use existing capabilities as the platform for major leaps in terms of innovation, diversification, or internationalization

## Slide 3: Context The advantages & disadvantages of a Mergers and Acquisitions (M&A) Strategy.
Mergers and acquisitions Strategy
Description
Advantages
Disadvantages
Mergers and acquisitions (M&A) bring together companies through complete changes in ownership. It has been used by companies for centuries and remains a major way for companies to expand rapidly
Business extension: M&A can be used to extend the reach of a firm in terms of geography, products, or markets
Building capabilities: M&A may increase a company’s capabilities
Increase market power by reducing competition and increasing bargaining power with suppliers
Increase efficiency: by sharing resources and capabilities
Speed: M&A allows acquirers to act fast
Financial efficiency: by combining the 2 balance sheets
Tax efficiency
Important investment upfront
Potential culture clash between the 2 companies
High failure rate
Sometimes excessive initial valuations, exaggerated expectations of strategic fit, and underestimated problems of organizational fit

## Slide 4: The Mergers & Acquisitions (M&A) Life Cycle includes 6 phases:
Target Screening
Due Diligence
Transaction Execution
Post Merger Integration
Divestiture
M&A Strategy

## Slide 5: Main problem of the M&A Strategy More than half of Mergers & Acquisitions fail to reach their value creation objectives.
Chart: Mergers & Acquisitions’ ability to reach value creation objectives*
| Failure rate | Success rate
Mergers & Acquisitions’ ability to reach their value creation objectives | 0.55 | 0.45
*Consolidation of multiple surveys from New York Times, Harvard Business Review and Australia Financial Review

## Slide 6: Root cause of the problem A poorly managed post merger integration phase is responsible for more than half of Mergers & Acquisitions (M&A) failures.
*Consolidation of multiple surveys from New York Times, Harvard Business Review and Australian Financial Review
Chart: 
| Corporate Strategy definition | Target screening & Due diligence | Negotiation & closing | Post merger integration
Main reasons for M&A failure (%) | 0.09 | 0.25 | 0.14 | 0.52

## Slide 7: Traditional Solution To solve this problem, companies usually hire management consultants from tier-one management consulting firms. Whereas this solution works well, not everyone can afford it.
To help them increase the value creation of their mergers & acquisitions, most tier-one companies (e.g. Apple, Procter & Gamble, Google, Amazon, etc.) are hiring management consultants from the following management consulting firms:
Whereas this solution usually brings a tremendous return on investment, not every business can afford to spend $300k+ to hire of couple of McKinsey, Deloitte or BCG Management Consultants.

## Slide 8: Our Solution Our management consulting firm decided to create an affordable Post Merger Integration Toolkit that will help you increase the value creation of the mergers & acquisitions of your organization (or your client if you are a management consultant).
The Post Merger Integration Toolkit includes:
Toolkits
Tools
Templates
Step-by-step Tutorials
Real-life Examples
Best Practices
Support from Tier-1 Management Consultants
Frameworks

## Slide 9: Objectives The Post Merger Integration Toolkit includes frameworks, tools, templates, tutorials, real-life examples and best practices to help you:
  Conduct a post merger integration to ensure the company reach its cost and revenue synergy targets
  Increase the value creation of your mergers & acquisitions with a simple and comprehensive 3-phase approach: (I) Strategy & high-level plan, (II) Detailed plans, (III) Implementation & monitoring
  Define & communicate your post merger acquisition strategy & high-level plan: (1) Merger strategic objectives, (2) Integration management office, (3) Guiding principles, (4) Post merger integration high-level plan, (5) Top layer organizational structure, (6) Top management appointment, (7) Training to help managers set up their team, (8) Integrated synergy baseline, (9) Synergy targets, (10) Potential integration & synergy initiatives, (11) Business cases and financial models, (12) Integration & synergy initiatives prioritization
  Develop & communicate the detailed plans: (1) Day 1 readiness checklist, (2) Integration & synergy initiatives plan, (3) Change management strategy and plan, (4) Communication strategy and plan, (5) Culture integration strategy and plan, (6) Risk management strategy and plan, (7) Staffing & retention plan
  Implement and monitor the post merger integration high-level plan and detailed plans
  Institutionalize your PMI approach
  Become the post merger integration subject matter expert of your organization

## Slide 10: 3-Phase Approach The Post Merger Integration Toolkit includes a 3-Phase Approach that we built and refined over the past 20 years, by constant trial and error. The good news is that you don’t have to waste your time, energy and money going through that lengthy trial-and-error process. You can simply leverage our work and customize it based on the specificities of your organization.
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Post merger integration high-level plan status
Day 1 readiness checklist status
Integration & synergy initiatives plan status
Change management strategy and plan status
Communication strategy and plan status
Culture integration strategy and plan status
Risk management strategy and plan status
Staffing & retention plan status
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 11: In the next slides, you’ll see a small preview of the Phase 1
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Post merger integration high-level plan status
Day 1 readiness checklist status
Integration & synergy initiatives plan status
Change management strategy and plan status
Communication strategy and plan status
Culture integration strategy and plan status
Risk management strategy and plan status
Staffing & retention plan status
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 12: Our merger strategic objectives are:
1
Replace this text by your own text
2
Replace this text by your own text
3
Replace this text by your own text
4
Replace this text by your own text
5
Replace this text by your own text
6
Replace this text by your own text
Don’t reinvent the wheel here. Most of the strategic objectives should have already been written prior to the deal.
Template

## Slide 13: The most common merger strategic objectives are:
1
Gaining economies of scale
2
Entering a new country
3
Entering a new market
4
Increasing the company product or service portfolio
5
Increasing market share by acquiring one of your competitors (horizontal integration)
6
Becoming a key player in an industry by acquiring one of your suppliers or clients (vertical integration)
Example we used during a PMI consulting project we did for a Global Fortune 1000 firm.
Example

## Slide 14: We decided to create an Integration Management Office that will be responsible for the success of the integration
The Integration Management Office will oversee the post Merger Integration and be responsible for the success of the integration. It includes 7 [replace this number by your own number] executives representing both [insert name of the acquiring company] and [insert name of the acquired company]:
Integration Management Officer
[Insert name]
Integration and Synergy Initiatives
[Insert name]
Change Management
[Insert name]
Culture
[Insert name]
Risk Management
[Insert name]
Communication
[Insert name]
Training
[Insert name]
This is only an example. You may decide to emphasize different areas and adjust the size of the integration Management Office

## Slide 15: We identified 8 [insert your own number] post merger integration guiding principles
1
Insert your own guiding principle
2
Insert your own guiding principle
3
Insert your own guiding principle
4
Insert your own guiding principle
7
Insert your own guiding principle
5
Insert your own guiding principle
8
Insert your own guiding principle
6
Insert your own guiding principle
Template

## Slide 16: Top 8 post merger integration guiding principles commonly used
1
Be clear on the strategic objectives of the deal
2
Ground the integration in the objectives of the deal
3
Be clear on your synergy baseline and synergy targets
4
Create a robust integration plan to reach the strategic objectives of the deal and the synergy targets
7
Ensure cultural fit
5
Search for synergies in every function of the newly created organization
8
Maintain business momentum
6
Communicate on a regular basis to all stakeholders
Example we used during a PMI consulting project we did for a Global Fortune 1000 firm.
Example

## Slide 17: See below 4 screenshots from the Phase 1.
Screenshots
High-Level Plan - Phase 1
Prioritization Matrix
Lean Business Case
Synergy Target Breakdown

## Slide 18: In the next slides, you’ll see a small preview of the Phase 2.
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Post merger integration high-level plan status
Day 1 readiness checklist status
Integration & synergy initiatives plan status
Change management strategy and plan status
Communication strategy and plan status
Culture integration strategy and plan status
Risk management strategy and plan status
Staffing & retention plan status
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 19: Day 1 Readiness Checklist
illustration
 | Owner | Due date | Status | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 0
Prepare internal communications | AD | March 12 | Done |  |  |  |  |  |  |  |  |  | 
Prepare external communications | Aurelien F. | Jan 20 | Done |  |  |  |  |  |  |  |  |  | 
Define pricing policy | Christian G. | Feb 28 | Done |  |  |  |  |  |  |  |  |  | 
Integrate General ledger | George P. | March 31 | Done |  |  |  |  |  |  |  |  |  | 
Prepare welcome drink for new employees | George P. | March 31 | On Track |  |  |  |  |  |  |  |  |  | 
Adjust sales pitch | Christian G. | March 31 | Late |  |  |  |  |  |  |  |  |  | 
Align marketing messages | George P. | March 31 | On Track |  |  |  |  |  |  |  |  |  | 
Define the synergy targets | George P. | March 31 | Late |  |  |  |  |  |  |  |  |  | 
Integrate brands |  |  | On Track |  |  |  |  |  |  |  |  |  | 
Integrate products & services |  |  | On Track |  |  |  |  |  |  |  |  |  | 
Integrate reporting |  |  | On Track |  |  |  |  |  |  |  |  |  | 
Define employee retention strategy |  |  | Late |  |  |  |  |  |  |  |  |  | 
Rationalize employee compensations |  |  | Late |  |  |  |  |  |  |  |  |  | 
Insert name of activity |  |  | Late |  |  |  |  |  |  |  |  |  | 
Weeks

## Slide 20: The Day-1 Readiness Checklist often includes many activities that will better fit in an Excel document
Open the Excel document “1b. Day-1 Readiness Checklist” for more details

## Slide 21: See below 4 additional screenshots from the Phase 2.
Screenshots
Change Impact Assessment Matrix
Stakeholder Analysis Matrix
Communication Strategy & Plan
Culture Integration Strategy

## Slide 22: In the next slides, you’ll see a small preview of the Phase 3.
Phase I: Define & Communicate the Strategy & High-Level Plan
Phase II: Develop & Communicate the Detailed Plans
Phase III: Implement & Monitor
Merger strategic objectives
Integration management office
Guiding principles
Post merger integration high-level plan
Organizational structure (Top layers)
Top management appointment
Training to help managers set up their team
Integrated synergy baseline
Synergy targets
Potential integration & synergy initiatives
Business cases and financial models
Integration & synergy initiatives prioritization
Post merger integration high-level plan status
Day 1 readiness checklist status
Integration & synergy initiatives plan status
Change management strategy and plan status
Communication strategy and plan status
Culture integration strategy and plan status
Risk management strategy and plan status
Staffing & retention plan status
Integration lessons learned
Institutionalization of the updated PMI Toolkit
Day 1 readiness checklist
Integration & synergy initiatives plan
Change management strategy and plan
Communication strategy and plan
Culture integration strategy and plan
Risk management strategy and plan
Staffing & retention plan

## Slide 23: To ensure a proper execution of the integration & synergy initiatives, it is very important to appoint high-caliber initiative owner or project manager
Project Manager
Quality
Cost
Time
Meeting the expectations
Managing a budget and resource limitations
Completing the project in a specific time of frame

The main challenge of the different initiative owners or project managers will be to meet the objectives while balancing the triple constraints of quality, cost and time

## Slide 24: See below 4 additional screenshots from the Phase 3.
Screenshots
Governance
Risk Management Framework
Initiative Status Report
Communication Plan

## Slide 25: Structure of the Toolkit The Post Merger Integration Toolkit includes 370 Powerpoint slides and 38 Excel sheets categorized in 4 folders that you can download on your device immediately after your purchase.
1
2
3
4
Overview and 3-phase approach
Phase I - Define & Communicate the Strategy & High-Level Plan
Phase II - Develop & Communicate the Detailed Plans
Phase III - Implement & Monitor
370 editable Powerpoint slides*
38 editable Excel sheets*
+
  *Please note that the number of Powerpoint slides and Excel sheets listed is the number of unique slides and sheets. For example, a Powerpoint slide that has been duplicated to facilitate the understanding of our clients only count for 1 Powerpoint slide.

## Slide 26: Interested in more than 1 Toolkit? You can access to all our Toolkits for half the price with the Gold Business & Consulting Package
www.slidebooks.com
Gold Business & Consulting Package
Learn More

## Slide 27: Key Benefits of our Business & Consulting Toolkits
Improve the growth & efficiency of your organization by leveraging Business & Consulting Toolkits created by ex-McKinsey, Deloitte & BCG Consultants.
It cost us $500k+ to create all our Business & Consulting Toolkits. Get them for a fraction of this cost.
It’s like hiring Management Consultants to create all the practical Frameworks, Tools & Templates required to get a competitive advantage.
Get the job done quicker and never start from scratch again with our ready-made & fully editable Frameworks, Tools & Templates in Powerpoint & Excel.
We have worked 20,000+ hours over the past 5 years to create the world’s best Business & Consulting Toolkits. Don’t reinvent the wheel. Download now.
Improve your skills & capabilities and meet your professional goals by learning how the Fortune 100 and Global Consulting Firms do it.
Get free support and advice from our ex-McKinsey, Deloitte & BCG Management Consultants.
Hiring top-tier Consultants for a management consulting project would cost you $300k+. A lot more expensive than purchasing our Toolkits.
Impress your stakeholders and become your organization’s subject matter expert with world-class approaches to resolve common business problems.

## Slide 28: What our clients say about our Toolkits Review imported from Facebooks, Amazon and Klaviyo
See more reviews >

## Slide 29: Join the 200,000+ Executives, Consultants & Entrepreneurs leveraging our Business & Consulting Toolkits to improve the performance of their organization and boost their own career.
Trusted by small and large organizations
Customer satisfaction
Number of countries leveraging our Business & Consulting Toolkits
160+
Number of professionals leveraging our Business & Consulting Toolkits
200,000+
4.8
Daily rate of our ex-McKinsey, Deloitte and BCG Management Consultants
$3k - $4k

## Slide 30: This was only a small preview.
www.slidebooks.com